## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to enter event details (type, location, budget, guests) so that the system can generate an event plan. | MUST HAVE | None | Jesmaa E | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a system, I want to validate user inputs before processing them. | MUST HAVE | US-01 | Jesmaa E | 3- Completed
Sprint 1 | Sprint 1 | US-03 | As a system, I want to initialize and coordinate multiple AI agents. | MUST HAVE | US-02 | Jesmaa E | 3- Completed
Sprint 1 | Sprint 1 | US-04 | As a system, I want the Decision Agent to evaluate recommendations from all agents. | MUST HAVE | US-03 | Jesmaa E | 3- Completed
Sprint 1 | Sprint 1 | US-05 | As a system, I want to validate venue capacity against guest count. | MUST HAVE | US-04 | Jesmaa E | 3- Completed
Sprint 2 | Sprint 2 | US-06 | As a system, I want to validate the total event cost against the user's budget. | MUST HAVE | US-05 | Jesmaa E | 3- Completed
Sprint 2 | Sprint 2 | US-07 | As a system, I want to handle Gemini/API failures gracefully. | SHOULD HAVE | US-04 | Jesmaa E | 3- Completed
Sprint 2 | Sprint 2 | US-08 | As a user, I want to receive the final event plan in the terminal. | MUST HAVE | US-06, US-07 | Jesmaa E | 3- Completed
Sprint 2 | Sprint 2 | US-09 | As a developer, I want to perform unit testing and fix defects before deployment. | SHOULD HAVE | US-08 | Jesmaa E | 3- Completed
Sprint 2 | Sprint 2 | US-10 | As a developer, I want to prepare project documentation and reports. | SHOULD HAVE | US-09 | Jesmaa E | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7