## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Jesmaa E | 2026-07-01 | User input accepted with empty event type | Sprint 1 | Jesmaa E | Logical | Added mandatory input validation | 2026-07-02 | Closed | Resolved
2 | Jesmaa E | 2026-07-03 | Invalid budget values caused incorrect calculations | Sprint 1 | Jesmaa E | Logical | Added numeric validation for budget | 2026-07-04 | Closed | Resolved
3 | Jesmaa E | 2026-07-05 | AI agent failed when location input was missing | Sprint 1 | Jesmaa E | User Interface | Added null value checks | 2026-07-06 | Closed | Resolved
4 | Jesmaa E | 2026-07-07 | Decision Agent selected unsuitable venue | Sprint 1 | Jesmaa E | Logical | Improved decision rules | 2026-07-08 | Closed | Resolved
5 | Jesmaa E | 2026-07-09 | Venue capacity validation was skipped | Sprint 2 | Jesmaa E | User Interface | Added capacity validation before selection | 2026-07-10 | Closed | Resolved
6 | Jesmaa E | 2026-07-13 | Total event cost exceeded user budget | Sprint 2 | Jesmaa E | Logical | Implemented budget validation | 2026-07-14 | Closed | Resolved
7 | Jesmaa E | 2026-07-15 | Gemini API timeout caused application failure | Sprint 2 | Jesmaa E | Maintainability | Implemented budget validation | 2026-07-16 | Closed | Resolved
8 | Jesmaa E | 2026-07-17 | Unexpected AI response caused parsing error | Sprint 2 | Jesmaa E | Logical | Added response validation | 2026-07-18 | Closed | Resolved
9 | Jesmaa E | 2026-07-20 | Final event summary displayed incomplete details | Sprint 2 | Jesmaa E | Maintainability | Updated output formatting | 2026-07-21 | Closed | Resolved
10 | Jesmaa E | 2026-07-22 | Application terminated on invalid API response | Sprint 2 | Jesmaa E | Maintainability | Added fallback response and error handling | 2026-07-23 | Closed | Resolved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others